## Project
field | value
project_id | HERO-BAT-HU-001
project_name | BatteryCo Hungary EV Battery Manufacturing Complex (Synthetic Hero Project)
country | Hungary
region | Northeast Hungary (synthetic site; not modeled on any specific existing town or real project)
industry | EV battery manufacturing (cell + module/pack)
project_type | Greenfield factory construction + production-line commissioning
planned_start | 2025-01-06
planned_completion | 2027-12-21
currency | USD
description | SYNTHETIC benchmark project. A fictional Korean battery manufacturer ('BatteryCo') builds a greenfield EV battery cell and module/pack manufacturing complex in Hungary, from feasibility study through construction, equipment installation, commissioning, and start of production. This project and all of its tasks, dates, costs, and companies are synthetic and were generated to serve as a realistic benchmark input for the REPLAN agent; it is not a record of any real company's project and does not reproduce the history of any real-world case in data/l3_ground_truth/.
data_origin | SYNTHETIC

## WBS
task_id | wbs_code | phase | task_name | task_description | owner_company | owner_type | country | region | planned_start | planned_end | duration_days | predecessor_ids | dependency_type | planned_cost | currency | criticality | risk_tags | milestone | milestone_name | status | data_origin | origin_country | customs_required | permit_required
T001 | 1.1 | Project Initiation | Feasibility study | Techno-economic feasibility study for an overseas battery cell and module manufacturing complex. | BatteryCo | Project Owner | South Korea | Gyeonggi-do, South Korea (BatteryCo HQ, synthetic) | 2025-01-06 | 2025-02-05 | 30 |  |  | 300000 | USD | critical |  | FALSE |  | planned | SYNTHETIC
T002 | 1.2 | Project Initiation | Site selection | Evaluate and select the Hungarian industrial site for the plant. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2025-02-05 | 2025-03-22 | 45 | T001 | FS | 250000 | USD | high |  | FALSE |  | planned | SYNTHETIC
T003 | 1.3 | Project Initiation | Project financing & insurance close | Close project financing package and construction-phase insurance. | BatteryCo | Project Owner | South Korea | Gyeonggi-do, South Korea (BatteryCo HQ, synthetic) | 2025-02-05 | 2025-03-27 | 50 | T001 | FS | 100000 | USD | critical |  | FALSE |  | planned | SYNTHETIC
T004 | 1.4 | Project Initiation | Local partner / contractor selection | Select the EPC general contractor and local civil contractor. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2025-02-05 | 2025-03-17 | 40 | T002 | SS | 150000 | USD | low |  | FALSE |  | planned | SYNTHETIC
T005 | 1.5 | Project Initiation | Land acquisition | Acquire the selected industrial land parcel. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2025-03-27 | 2025-05-26 | 60 | T002,T003 | FS | 8000000 | USD | critical | regulation | TRUE | Land acquired | planned | SYNTHETIC
T006 | 2.1 | Regulation & Engineering | Environmental baseline survey | Baseline ecological and hydrological survey of the site. | Environmental Consultant | Consultant | Hungary | Northeast Hungary (synthetic site) | 2025-05-26 | 2025-06-30 | 35 | T005 | FS | 120000 | USD | critical | regulation | FALSE |  | planned | SYNTHETIC
T007 | 2.2 | Regulation & Engineering | Environmental impact review | Formal environmental impact assessment submitted to the regulator. | Environmental Consultant | Consultant | Hungary | Northeast Hungary (synthetic site) | 2025-06-30 | 2025-08-29 | 60 | T006 | FS | 200000 | USD | critical | regulation, permitting | FALSE |  | planned | SYNTHETIC
T008 | 2.3 | Regulation & Engineering | Environmental permit approval | Regulatory approval of the environmental permit. | Regulatory Authority | Regulatory Authority | Hungary | Northeast Hungary (synthetic site) | 2025-08-29 | 2025-10-13 | 45 | T007 | FS | 80000 | USD | critical | regulation, permitting | TRUE | Environmental permit approved | planned | SYNTHETIC
T009 | 2.4 | Regulation & Engineering | Geotechnical survey | Soil and foundation-bearing capacity survey of the site. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2025-05-26 | 2025-06-20 | 25 | T005 | FS | 90000 | USD | medium |  | FALSE |  | planned | SYNTHETIC
T010 | 2.5 | Regulation & Engineering | Utility agreement negotiation | Negotiate grid connection capacity and water supply agreement. | Utility Provider | Utility Provider | Hungary | Northeast Hungary (synthetic site) | 2025-05-26 | 2025-07-15 | 50 | T005 | FS | 60000 | USD | low | utility, regulation | FALSE |  | planned | SYNTHETIC
T011 | 2.6 | Regulation & Engineering | Detailed engineering design | Detailed civil, structural, and MEP engineering design package. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2025-06-20 | 2025-09-18 | 90 | T009,T004 | FS | 1800000 | USD | medium |  | FALSE |  | planned | SYNTHETIC
T012 | 2.7 | Regulation & Engineering | Construction permit application & approval | Submit and obtain the building/construction permit from the regulator. | Regulatory Authority | Regulatory Authority | Hungary | Northeast Hungary (synthetic site) | 2025-10-13 | 2025-12-22 | 70 | T011,T008 | FS | 100000 | USD | critical | regulation, permitting | TRUE | Construction permit approved | planned | SYNTHETIC |  |  | 예
T013 | 2.8 | Regulation & Engineering | Local regulatory approval | Final zoning and building-code sign-off from local authorities. | Regulatory Authority | Regulatory Authority | Hungary | Northeast Hungary (synthetic site) | 2025-12-22 | 2026-01-21 | 30 | T012 | FS | 40000 | USD | low | regulation, permitting | FALSE |  | planned | SYNTHETIC |  |  | 예
T014 | 3.1 | Procurement | Major equipment specification & vendor selection | Finalize process equipment specifications and select equipment vendors. | BatteryCo | Project Owner | South Korea | Gyeonggi-do, South Korea (BatteryCo HQ, synthetic) | 2025-06-20 | 2025-08-04 | 45 | T011 | SS | 200000 | USD | low |  | FALSE |  | planned | SYNTHETIC
T015 | 3.2 | Procurement | Long-lead cell equipment order | Place order for long-lead cell production equipment (coating, winding, assembly). | Equipment Vendor A | Equipment Vendor | South Korea | Gyeonggi-do, South Korea (BatteryCo HQ, synthetic) | 2025-08-04 | 2025-09-03 | 30 | T014 | FS | 15000000 | USD | low | equipment, supply_chain | TRUE | Long-lead equipment ordered | planned | SYNTHETIC | South Korea
T016 | 3.3 | Procurement | Long-lead module/pack equipment order | Place order for long-lead module and pack assembly/automation equipment. | Equipment Vendor B | Equipment Vendor | Germany | Bavaria, Germany (Equipment Vendor B HQ, synthetic) | 2025-08-04 | 2025-09-03 | 30 | T014 | FS | 12000000 | USD | low | equipment, supply_chain | FALSE |  | planned | SYNTHETIC | Germany
T017 | 3.4 | Procurement | Electrical equipment procurement | Procure transformers, switchgear, and electrical distribution equipment. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-01-21 | 2026-03-02 | 40 | T013 | FS | 3000000 | USD | low | equipment, supply_chain | FALSE |  | planned | SYNTHETIC
T018 | 3.5 | Procurement | Mechanical/HVAC equipment procurement | Procure HVAC, compressed air, and mechanical utility equipment. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-01-21 | 2026-03-02 | 40 | T013 | FS | 2500000 | USD | low | equipment, supply_chain | FALSE |  | planned | SYNTHETIC
T019 | 3.6 | Procurement | Construction material procurement | Procure structural steel, concrete, and building cladding materials. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-01-21 | 2026-02-25 | 35 | T013 | FS | 4000000 | USD | low | supply_chain, logistics | FALSE |  | planned | SYNTHETIC
T020 | 3.7 | Procurement | Logistics & customs planning | Plan international shipping routes and pre-register customs documentation. | Logistics Partner | Logistics Provider | Hungary | Northeast Hungary (synthetic site) | 2025-08-04 | 2025-09-03 | 30 | T015,T016 | SS | 80000 | USD | low | logistics, customs | FALSE |  | planned | SYNTHETIC
T021 | 4.1 | Site & Civil Construction | Site preparation & clearing | Clear vegetation, grade, and prepare the construction site. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2025-12-22 | 2026-01-31 | 40 | T012 | FS | 900000 | USD | critical | permitting, construction, regulation | TRUE | Site cleared | planned | SYNTHETIC
T022 | 4.2 | Site & Civil Construction | Ground improvement / soil stabilization | Soil stabilization and compaction ahead of foundation work. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-01-31 | 2026-03-07 | 35 | T021 | FS | 700000 | USD | critical | construction, weather | FALSE |  | planned | SYNTHETIC
T023 | 4.3 | Site & Civil Construction | Foundation & underground utility trenching | Pour foundations and trench for underground utility routing. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-03-07 | 2026-05-01 | 55 | T022 | FS | 2200000 | USD | critical | construction, weather, labor | FALSE |  | planned | SYNTHETIC
T024 | 4.4 | Site & Civil Construction | Structural steel erection (go-vertical) | Erect the primary structural steel frame of the main building. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-05-01 | 2026-07-10 | 70 | T023 | FS | 5500000 | USD | critical | construction, labor, weather, supply_chain | TRUE | Structure topped out (go-vertical) | planned | SYNTHETIC
T025 | 4.5 | Site & Civil Construction | Roofing & building enclosure | Install roofing and exterior wall cladding to fully enclose the building. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-07-10 | 2026-08-19 | 40 | T024 | FS | 1800000 | USD | critical | construction, weather | TRUE | Building enclosed | planned | SYNTHETIC
T026 | 4.6 | Site & Civil Construction | Internal civil works | Interior flooring, partitions, and finishes. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-08-19 | 2026-10-03 | 45 | T025 | FS | 1400000 | USD | high | construction, labor | FALSE |  | planned | SYNTHETIC
T027 | 4.7 | Site & Civil Construction | Site paving, fencing & security infrastructure | Exterior paving, perimeter fencing, and security infrastructure. | Local Civil Contractor | Civil Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-05-01 | 2026-05-31 | 30 | T024 | SS | 500000 | USD | low | construction | FALSE |  | planned | SYNTHETIC
T028 | 5.1 | Utilities & Facility | Grid connection construction | Build the medium-voltage grid connection line to the site. | Utility Provider | Utility Provider | Hungary | Northeast Hungary (synthetic site) | 2026-05-01 | 2026-06-30 | 60 | T010,T023 | FS | 2000000 | USD | low | utility, regulation | FALSE |  | planned | SYNTHETIC
T029 | 5.2 | Utilities & Facility | Substation installation | Install and energize the on-site substation. | Utility Provider | Utility Provider | Hungary | Northeast Hungary (synthetic site) | 2026-06-30 | 2026-08-19 | 50 | T028 | FS | 3500000 | USD | low | utility, equipment | TRUE | Substation energized | planned | SYNTHETIC |  |  | 예
T030 | 5.3 | Utilities & Facility | Water supply connection | Connect municipal/industrial water supply to the site. | Utility Provider | Utility Provider | Hungary | Northeast Hungary (synthetic site) | 2026-05-01 | 2026-06-10 | 40 | T010,T023 | FS | 500000 | USD | low | utility | FALSE |  | planned | SYNTHETIC
T031 | 5.4 | Utilities & Facility | Wastewater treatment system | Install on-site industrial wastewater treatment system. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-08-19 | 2026-10-03 | 45 | T025 | FS | 900000 | USD | low | utility, regulation | FALSE |  | planned | SYNTHETIC
T032 | 5.5 | Utilities & Facility | HVAC installation | Install building HVAC and compressed dry-air systems. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-08-19 | 2026-10-08 | 50 | T025,T018 | FS | 2600000 | USD | critical | equipment, construction | FALSE |  | planned | SYNTHETIC
T033 | 5.6 | Utilities & Facility | Fire protection system installation | Install fire suppression and detection systems. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-08-19 | 2026-09-23 | 35 | T025 | FS | 1100000 | USD | low | regulation, construction | FALSE |  | planned | SYNTHETIC
T034 | 5.7 | Utilities & Facility | Clean/dry room infrastructure | Build the low-humidity dry room shell required for cell production. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-10-08 | 2026-12-02 | 55 | T026,T032 | FS | 4200000 | USD | critical | equipment, construction | TRUE | Dry room enclosure completed | planned | SYNTHETIC
T035 | 5.8 | Utilities & Facility | Utility commissioning | Integrated test of grid, water, and HVAC systems together. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2026-10-08 | 2026-11-02 | 25 | T029,T030,T032,T033 | FS | 300000 | USD | low | utility | FALSE |  | planned | SYNTHETIC
T036 | 6.1 | Manufacturing Equipment | Cell equipment manufacturing | Fabrication of cell production equipment at the vendor's home factory. | Equipment Vendor A | Equipment Vendor | South Korea | Gyeonggi-do, South Korea (BatteryCo HQ, synthetic) | 2025-09-03 | 2026-01-01 | 120 | T015 | FS | 2000000 | USD | low | equipment, supply_chain | FALSE |  | planned | SYNTHETIC | South Korea
T037 | 6.2 | Manufacturing Equipment | Module/pack equipment manufacturing | Fabrication of module and pack assembly equipment at the vendor's home factory. | Equipment Vendor B | Equipment Vendor | Germany | Bavaria, Germany (Equipment Vendor B HQ, synthetic) | 2025-09-03 | 2025-12-22 | 110 | T016 | FS | 1800000 | USD | low | equipment, supply_chain | FALSE |  | planned | SYNTHETIC | Germany
T038 | 6.3 | Manufacturing Equipment | Factory acceptance test - cell equipment | FAT of cell production equipment at the vendor's facility. | Equipment Vendor A | Equipment Vendor | South Korea | Gyeonggi-do, South Korea (BatteryCo HQ, synthetic) | 2026-01-01 | 2026-01-21 | 20 | T036 | FS | 150000 | USD | low | equipment | TRUE | Cell equipment FAT passed | planned | SYNTHETIC | South Korea
T039 | 6.4 | Manufacturing Equipment | Factory acceptance test - module equipment | FAT of module/pack equipment at the vendor's facility. | Equipment Vendor B | Equipment Vendor | Germany | Bavaria, Germany (Equipment Vendor B HQ, synthetic) | 2025-12-22 | 2026-01-11 | 20 | T037 | FS | 140000 | USD | low | equipment | FALSE |  | planned | SYNTHETIC | Germany
T040 | 6.5 | Manufacturing Equipment | International shipping - cell equipment | Ocean/inland freight of cell equipment from South Korea to Hungary. | Logistics Partner | Logistics Provider | Hungary | South Korea -> Hungary (in transit) | 2026-01-21 | 2026-02-25 | 35 | T038,T020 | FS | 800000 | USD | low | logistics, supply_chain | FALSE |  | planned | SYNTHETIC | South Korea | 예
T041 | 6.6 | Manufacturing Equipment | International shipping - module equipment | Freight of module/pack equipment from Germany to Hungary. | Logistics Partner | Logistics Provider | Hungary | Germany -> Hungary (in transit) | 2026-01-11 | 2026-01-26 | 15 | T039,T020 | FS | 300000 | USD | low | logistics, supply_chain | FALSE |  | planned | SYNTHETIC | Germany | 아니오
T042 | 6.7 | Manufacturing Equipment | Customs clearance - cell equipment | Import customs clearance for cell equipment at the Hungarian border/port. | Logistics Partner | Logistics Provider | Hungary | Northeast Hungary (synthetic site) | 2026-02-25 | 2026-03-07 | 10 | T040 | FS | 60000 | USD | low | customs, logistics, regulation | FALSE |  | planned | SYNTHETIC | South Korea | 예
T043 | 6.8 | Manufacturing Equipment | Customs clearance - module equipment | Import customs clearance for module/pack equipment. | Logistics Partner | Logistics Provider | Hungary | Northeast Hungary (synthetic site) | 2026-01-26 | 2026-02-03 | 8 | T041 | FS | 40000 | USD | low | customs, logistics, regulation | FALSE |  | planned | SYNTHETIC | Germany | 아니오
T044 | 6.9 | Manufacturing Equipment | Inland transportation to site | Inland trucking of cleared equipment from the border/port to the site. | Logistics Partner | Logistics Provider | Hungary | Northeast Hungary (synthetic site) | 2026-03-07 | 2026-03-12 | 5 | T042,T043 | FS | 50000 | USD | low | logistics | FALSE |  | planned | SYNTHETIC
T045 | 6.10 | Manufacturing Equipment | Equipment delivery to site | Final delivery and site receiving of all manufacturing equipment. | Logistics Partner | Logistics Provider | Hungary | Northeast Hungary (synthetic site) | 2026-12-02 | 2026-12-05 | 3 | T044,T034 | FS | 30000 | USD | critical | logistics, equipment | TRUE | Equipment delivered | planned | SYNTHETIC
T046 | 6.11 | Manufacturing Equipment | Equipment installation - cell line (mechanical) | Mechanical installation of cell production line equipment. | Equipment Vendor A | Equipment Vendor | Hungary | Northeast Hungary (synthetic site) | 2026-12-05 | 2027-01-19 | 45 | T045 | FS | 1200000 | USD | critical | equipment, labor | FALSE |  | planned | SYNTHETIC
T047 | 6.12 | Manufacturing Equipment | Equipment installation - module/pack line (mechanical) | Mechanical installation of module/pack line equipment. | Equipment Vendor B | Equipment Vendor | Hungary | Northeast Hungary (synthetic site) | 2026-12-05 | 2027-01-09 | 35 | T045 | FS | 900000 | USD | high | equipment, labor | FALSE |  | planned | SYNTHETIC
T048 | 6.13 | Manufacturing Equipment | Mechanical hookup | Process piping and gas-line hookup for both production lines. | Equipment Vendor A | Equipment Vendor | Hungary | Northeast Hungary (synthetic site) | 2027-01-19 | 2027-02-13 | 25 | T046,T047 | FS | 500000 | USD | critical | equipment, construction | FALSE |  | planned | SYNTHETIC
T049 | 6.14 | Manufacturing Equipment | Electrical hookup | Electrical hookup of production equipment to plant power distribution. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2027-02-13 | 2027-03-10 | 25 | T048,T035 | FS | 700000 | USD | critical | equipment, utility, labor | FALSE |  | planned | SYNTHETIC
T050 | 6.15 | Manufacturing Equipment | Automation & controls integration | Integrate line automation, MES, and controls systems. | Automation Integrator | Systems Integrator | Hungary | Northeast Hungary (synthetic site) | 2027-03-10 | 2027-04-09 | 30 | T049 | FS | 1000000 | USD | critical | equipment, labor | FALSE |  | planned | SYNTHETIC
T051 | 6.16 | Manufacturing Equipment | Equipment calibration | Calibrate and pre-qualify installed equipment prior to commissioning. | Equipment Vendor A | Equipment Vendor | Hungary | Northeast Hungary (synthetic site) | 2027-04-09 | 2027-04-29 | 20 | T050 | FS | 400000 | USD | critical | equipment | TRUE | Equipment installation complete | planned | SYNTHETIC
T052 | 7.1 | Commissioning | Facility inspection (pre-commissioning) | Joint EPC/regulator inspection ahead of formal commissioning. | Global EPC | EPC Contractor | Hungary | Northeast Hungary (synthetic site) | 2027-04-29 | 2027-05-14 | 15 | T051 | FS | 80000 | USD | critical | regulation | FALSE |  | planned | SYNTHETIC
T053 | 7.2 | Commissioning | Equipment commissioning - cell line | Commission the cell production line with vendor support. | Equipment Vendor A | Equipment Vendor | Hungary | Northeast Hungary (synthetic site) | 2027-05-14 | 2027-06-13 | 30 | T052 | FS | 600000 | USD | critical | equipment, labor | FALSE |  | planned | SYNTHETIC
T054 | 7.3 | Commissioning | Equipment commissioning - module/pack line | Commission the module/pack line with vendor support. | Equipment Vendor B | Equipment Vendor | Hungary | Northeast Hungary (synthetic site) | 2027-05-14 | 2027-06-08 | 25 | T052 | FS | 500000 | USD | high | equipment, labor | FALSE |  | planned | SYNTHETIC
T055 | 7.4 | Commissioning | Integrated line testing | End-to-end integrated test from cell production through module/pack. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2027-06-13 | 2027-07-08 | 25 | T053,T054 | FS | 450000 | USD | critical | equipment, labor | FALSE |  | planned | SYNTHETIC
T056 | 7.5 | Commissioning | Safety inspection | Regulator safety inspection of the commissioned facility. | Regulatory Authority | Regulatory Authority | Hungary | Northeast Hungary (synthetic site) | 2027-07-08 | 2027-07-18 | 10 | T055 | FS | 30000 | USD | critical | regulation | FALSE |  | planned | SYNTHETIC
T057 | 7.6 | Commissioning | Regulatory inspection & operating license approval | Final regulatory inspection and operating license issuance. | Regulatory Authority | Regulatory Authority | Hungary | Northeast Hungary (synthetic site) | 2027-07-18 | 2027-08-07 | 20 | T056 | FS | 50000 | USD | critical | regulation, permitting | TRUE | Commissioning completed / operating license granted | planned | SYNTHETIC |  |  | 예
T058 | 8.1 | Production Launch | Workforce recruitment & training | Recruit and train the production workforce. | Workforce Agency | Labor/HR Partner | Hungary | Northeast Hungary (synthetic site) | 2026-10-08 | 2026-12-07 | 60 | T034 | SS | 700000 | USD | low | labor | FALSE |  | planned | SYNTHETIC
T059 | 8.2 | Production Launch | Trial production - cell line | Initial trial production runs on the cell line. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2027-08-07 | 2027-09-06 | 30 | T057,T058 | FS | 900000 | USD | critical | labor, equipment, regulation | TRUE | Trial production started | planned | SYNTHETIC
T060 | 8.3 | Production Launch | Trial production - module/pack line | Initial trial production runs on the module/pack line. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2027-08-07 | 2027-09-01 | 25 | T057,T058 | FS | 700000 | USD | high | labor, equipment | FALSE |  | planned | SYNTHETIC
T061 | 8.4 | Production Launch | Process qualification | Qualify the production process against quality specifications. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2027-09-06 | 2027-10-01 | 25 | T059,T060 | FS | 400000 | USD | critical | equipment, labor | FALSE |  | planned | SYNTHETIC
T062 | 8.5 | Production Launch | Yield stabilization | Stabilize production yield to target levels. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2027-10-01 | 2027-11-05 | 35 | T061 | FS | 500000 | USD | critical | equipment, labor | FALSE |  | planned | SYNTHETIC
T063 | 8.6 | Production Launch | Ramp-up to nameplate capacity | Ramp production volume up to nameplate capacity. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2027-11-05 | 2027-12-20 | 45 | T062 | FS | 1200000 | USD | critical | labor, equipment, supply_chain | FALSE |  | planned | SYNTHETIC
T064 | 8.7 | Production Launch | Start of production (SOP) | Formal start-of-production milestone. | BatteryCo | Project Owner | Hungary | Northeast Hungary (synthetic site) | 2027-12-20 | 2027-12-21 | 1 | T063 | FS | 0 | USD | critical |  | TRUE | Start of Production (SOP) | planned | SYNTHETIC

## Partners
company_id | company_name | company_type | responsibility | country
C01 | BatteryCo | Project Owner | Overall project ownership, financing, and plant operation | South Korea
C02 | Global EPC | EPC Contractor | Engineering, procurement, and construction management | Hungary (local office)
C03 | Local Civil Contractor | Civil Contractor | Site works, foundation, structural and civil construction | Hungary
C04 | Equipment Vendor A | Equipment Vendor | Cell production equipment manufacturing, delivery, and installation | South Korea
C05 | Equipment Vendor B | Equipment Vendor | Module/pack assembly equipment manufacturing, delivery, and installation | Germany
C06 | Logistics Partner | Logistics Provider | International shipping, customs clearance, and inland transportation | Hungary
C07 | Utility Provider | Utility Provider | Grid connection, substation, and water supply | Hungary
C08 | Regulatory Authority | Regulatory Authority | Environmental and construction permitting, safety and operating-license inspections | Hungary
C09 | Environmental Consultant | Consultant | Environmental baseline survey and impact assessment | Hungary
C10 | Automation Integrator | Systems Integrator | Production line automation, MES, and controls integration | Hungary
C11 | Workforce Agency | Labor/HR Partner | Local workforce recruitment and training | Hungary

## Risk Profile
risk_category | related_phase | monitoring_target | geography | rationale
regulation / permitting | Regulation & Engineering | Environmental/construction permit status; permitting-regime or exemption changes; inspection holds | Hungary (national and regional regulator) | L3 evidence (e.g. case V3-006, a Hungarian battery-plant permitting case) shows permitting-regime changes and safety-driven suspensions can delay trial/mass production by several months.
labor | Manufacturing Equipment / Commissioning | Specialized labor availability; work-authorization/visa status of vendor technicians on-site | Hungary (site) and equipment-vendor home countries (South Korea, Germany) | L3 evidence (e.g. cases V2-001 and V3-001, both labor-shortage/enforcement cases) shows labor disruptions can delay equipment installation and commissioning by 2-3 months or more.
weather / natural disaster | Site & Civil Construction | Severe weather events; grid emergency load-shed orders | Hungary (site) | L3 evidence (case V2-003, a severe winter storm) shows a single weather event can force a fab offline for 6+ weeks; civil construction phases are generally weather-sensitive.
logistics / customs | Manufacturing Equipment | International shipping schedule adherence; customs clearance duration | Vendor home countries to Hungary (in transit) | Equipment is shipped internationally from South Korea and Germany, exposing the schedule to shipping and customs delay risk (WBS tasks in the 6.5-6.9 range).
equipment | Manufacturing Equipment / Commissioning | Vendor equipment manufacturing/FAT schedule adherence; installation and calibration progress; process yield during ramp-up | Vendor home countries and site | L3 evidence (case V3-007, a repeatedly-restated fab timeline) shows equipment/process and funding-driven delays can compound into multi-year slips.
utility | Utilities & Facility | Grid connection agreement and substation energization schedule | Hungary (site) | Utility connection is a common construction dependency chain gating equipment hookup and commissioning; monitor grid capacity agreements and energization dates.
supply_chain | Procurement / Manufacturing Equipment | Construction material and component supply availability | Global | L3 evidence (cases V3-002/V3-003/V3-004, semiconductor-shortage cases) shows supply-chain shocks can idle production lines for days-to-weeks with a clear, well-documented numeric pattern.
contractor / construction | Site & Civil Construction | EPC/civil contractor schedule performance; capital-allocation and financing decisions | Hungary | L3 evidence (case V2-004) shows contractor/financial decisions can pause construction for 18+ months with an ambiguous, multi-milestone restart.
geopolitical / trade | Procurement | Export controls, tariffs, and tax-policy changes affecting equipment-vendor countries | Global (equipment-vendor countries) | L2 corpus records (e.g. RS-016 EV tax-credit policy change, RS-019 rare-earth export controls) show geopolitical/trade policy shifts can affect battery-sector project economics and supply chains.

## Procurement
item_id | item_name | supplier_id | origin_country | quantity | incoterms | customs_required | permit_or_certification | planned_arrival | needed_for_task_id
P-A1 | [합성] 셀 설비 1차 선적 서보 모터 자석 부품(희토류 자석 포함, 중국 공장 직송) | Equipment Vendor A | China | 1 | CIF | 예 | 원산지 증명 | 2026-03-07 | T044
P-A2 | [합성] 모듈·팩 설비 | Equipment Vendor B | Germany | 1 | DAP | 아니오 | CE 적합성 선언 | 2026-02-03 | T044
P-B | [합성] 셀 설비 교육 시뮬레이터 구동부(서보 모터·희토류 자석 포함) | Equipment Vendor A | China | 2 | DAP | 예 | 원산지 증명 | 2026-09-20 | T058
P-C | [합성] 셀 라인 교정용 정밀 서보 스테이지(희토류 자석 포함) | Equipment Vendor A | China | 1 | DAP | 예 | 원산지 증명, 교정 성적서 | 2027-03-26 | T051
P-D | [합성] 모듈 라인 시운전 예비 부품 | Equipment Vendor B | Germany | 1 | DAP | 아니오 | CE 적합성 선언 | 2027-04-30 | T054
P-E | [합성] 변전 설비(변압기·개폐기) | Utility Provider | Hungary | 2 | DDP | 아니오 | 계통 연계 승인 | 2026-06-15 | T029